## Issues
No | Description | Type (Bug/Improvement) | Code/UI | Priority
1 | ELEVENLABS_API_KEY is not set, so every AI-teacher lesson falls back to the device voice. One missing key silently changes the teacher's voice for every student. | Bug | Code | High
2 | 22,000 question images are hotlinked to media-mycbseguide.s3.amazonaws.com (a third party). If they block us or delete a file, thousands of diagrams disappear from the app the same day. | Bug | Code | High
3 | 7,639 question images have a bare filename as their src (e.g. "image.png") with no host, so they render as a blank box today. | Bug | Code | High
4 | Scores are lost silently when a submit fails. Brain Gym, Activities, Arena and MCQ results are POSTed with no retry and no queue - the student sees a score the server never recorded. | Bug | Code | High
5 | The Supabase database has NO backup of any kind. The free tier includes none, no script exists, and no dump has ever been taken. | Bug | Code | High
6 | The database is at 483 MB of the 500 MB free-tier limit (96.6%). Past the cap Supabase moves the project to read-only. | Bug | Code | High
7 | Announcements are published from the admin portal but the audience and schedule fields are not yet surfaced in the app beyond a Home banner (no scheduling UI, no per-class targeting UI). | Improvement | UI | High
8 | Maths content is mostly missing from the database - maths_questions is ~29% present against biology ~100% and physics ~95%. | Bug | Code | High
9 | A failed request waits the full 60-second timeout even when the phone has no network at all. The timeout is sized for Render's cold start, so an offline user stares at a spinner for a minute. | Improvement | Code | Medium
10 | No connectivity detection anywhere in the app (@react-native-community/netinfo is not installed), so the app cannot tell 'offline' from 'server slow'. | Improvement | Code | Medium
11 | No retry or backoff on Anthropic API calls. A 429 or 5xx from Claude fails straight through to a 502 the student sees. | Improvement | Code | Medium
12 | Render's free plan spins the service down after ~15 minutes idle, so the first request of the day pays a cold start of up to 50 seconds. A keep-alive ping would remove it. | Improvement | Code | Medium
13 | The subjects table contains duplicate rows - the same Hindi and Sanskrit subjects exist twice under two slugs, one of them random (e.g. 'uidbx0g'). Resources and Practice likely show each twice. | Bug | Code | Medium
14 | No PYQ content for classes 6-8. Class 7 has 0 of 327 chapters, class 8 has 0 of 342, class 6 has 11 of 292. Blocked on an examin8 login. | Bug | Code | Medium
15 | Class 10 revision notes cover only 44 of 318 chapters. Classes 6-9 are served from ncert_solutions part 4; class 10 uses the sections model and is mostly empty. | Bug | Code | Medium
16 | useApi<T> response types in the admin portal are hand-written per call site, so they can silently drift from what the server actually returns (this caused the class-filter crash). | Improvement | Code | Medium
17 | MSG91_AUTH_KEY is configured but the SMS path appears unused - phone OTP falls back to the dev path. Possibly paying for a service the app never calls. | Improvement | Code | Medium
18 | The Brevo SMTP key expires after 90 days of inactivity. Password resets are infrequent enough that this will happen, and it fails invisibly because /forgot-password answers identically either way. | Improvement | Code | Medium
19 | The app bundle is 51.8 MB because the reachable question banks ship inside it. The database now holds 88,950 practice questions, so most of the destination already exists. | Improvement | Code | Medium
20 | ~215 MB of src/data is unreachable from any screen. Removable only after a both-sides count against the database, and never for maths. | Improvement | Code | Medium
21 | Any-class browsing has never been tested on a device. Needs a pass across Practice, Resources, MCQ, online and mock tests for each class, confirming the free/paid lock is untouched. | Improvement | Code | Medium
22 | Releases are uploaded to Play by hand. An eas submit setup with a Play service account would stop the next 75-commit gap forming. | Improvement | Code | Medium
23 | Question images load from a CDN inside the 3D avatar viewer (jsdelivr/unpkg). A CDN outage or a changed file breaks the avatar. | Improvement | Code | Medium
24 | No web UI for the support queue. Staff must answer tickets from a phone even though the endpoints and socket.io rooms already exist. | Improvement | UI | Medium
25 | No web UI for error logs. The pipeline and the /admin/error-logs endpoint exist, but the only reader is inside the mobile app. | Improvement | UI | Medium
26 | Mr. Iker (the male AI teacher) is an SVG illustration rather than the HeyGen avatar. Swapping it in needs a HeyGen API key or any male portrait. | Improvement | UI | Low
27 | OTPScreen still uses barStyle="light-content" on a white background, so the status-bar icons are white on white. | Bug | UI | Low
28 | OTPScreen carries two leftover purple colour values (rgba(139,110,240)) from before the theme moved to white and gold. | Improvement | UI | Low
29 | 1,825 of the app's 1,911 image assets sit loose in the assets/ root with no folder structure, including at least one 2 MB duplicate named with a ' (1)' suffix. | Improvement | UI | Low
30 | Sort It Lab uses tap-then-tap rather than drag-and-drop. Faster with a thumb, but the reference design used dragging. | Improvement | UI | Low
31 | Assembled Class Game tiles show the four MCQ options as hint chips because they are derived from multiple-choice questions. Only curated activities can pose a genuinely open question. | Improvement | UI | Low
32 | Language and literature chapters get the same fact-recall activity format as Science. A comprehension-oriented mission set would suit Hindi, Sanskrit and English better. | Improvement | UI | Low
33 | Questions containing LaTeX or images are skipped by the activity assembler because a tile cannot render them. This affects Maths and Physics chapters most. | Improvement | Code | Low
34 | Curated activities can only be authored by running a seed script. An admin screen over upsertCurated would let content staff replace assembled activities without engineering. | Improvement | UI | Low
35 | No age gate or verifiable parental consent. The DPDP Act requires it for under-18s and most users are children. Needs product and legal input before it can be scoped. | Improvement | Code | Low
36 | Support chat reaches nobody outside working hours. An agent console, ticket routing and presence is the real feature. | Improvement | Code | Low

## How to use
Ailernova - Issue Tracker
Generated | 25 September 2026, from docs/BUG_LIST_2026-09-04.md and the 7-25 September working sessions.
Columns
No | Row number. Stable - a finished item keeps its number so a number quoted last week still points at the same thing.
Description | What the issue is, and why it matters. Written so someone who has not seen the codebase can judge it.
Type | Bug = something is broken. Improvement = it works but should be better, or is half-built.
Code/UI | Code = server, data or app logic. UI = layout, styling or a missing screen.
Priority | High = affects major functionality or is clearly visible to a user. Medium = not visible but must be fixed. Low = mostly cosmetic or UI.
Editing | Type, Code/UI and Priority are dropdowns - click the cell and pick a value. Add new rows at the bottom; the dropdowns already extend 200 rows down.
Note | Every item here was verified against the live database, the deployed server or the code - none are carried over unchecked.